## Frontend Internship Tasks
Task ID | Module | Task Title | Detailed Description | Required Skills | Difficulty | Expected Deliverables | Estimated Duration
1 | Project Setup | Initialize React Project Architecture | Create a scalable React project using Vite. Organize folders for components, pages, hooks, layouts, services, context, and utilities. Configure Tailwind CSS and React Router properly. | React, Vite, Tailwind CSS, React Router | Intermediate | Scalable frontend project setup with routing and styling. | 1 Day
2 | UI/UX | Build Responsive Navbar System | Develop a professional responsive navbar with dropdown menus, mobile sidebar, sticky behavior, route highlighting, and smooth transitions. | Responsive Design, React | Intermediate | Fully responsive production-ready navbar. | 1.5 Days
3 | State Management | Implement Global Cart System | Create a reusable cart management system using Context API with localStorage persistence, quantity controls, subtotal calculations, and reusable hooks. | Context API, localStorage | Intermediate | Global cart functionality across the application. | 2 Days
4 | Marketplace | Develop Advanced Product Listing Page | Build a dynamic marketplace page with filters, category tabs, sorting, pagination, skeleton loading, responsive cards, and search functionality. | React Components, Filtering, Pagination | Advanced | Enterprise-grade product listing experience. | 3 Days
5 | Marketplace | Create Product Details Experience | Design a premium product details page with image gallery, zoom effect, variants, pricing, reviews section, and related products. | UI/UX, Component Architecture | Advanced | High-quality eCommerce product page. | 2 Days
6 | Animations | Implement Smooth Animations | Use Framer Motion or AOS for page transitions, reveal animations, hover interactions, loading effects, and animated cards. | Framer Motion, AOS | Advanced | Modern animated user experience. | 2 Days
7 | Dashboard | Build Enterprise Dashboard Layout | Create a dashboard with collapsible sidebar, responsive layouts, reusable cards, analytics widgets, top navigation, and breadcrumbs. | Dashboard UI, Responsive Layouts | Advanced | Professional admin dashboard structure. | 3 Days
8 | CMS | Develop CMS Management Interface | Build forms and editors for managing hero sections, testimonials, products showcase, and promotions with image previews and reusable form components. | Forms, Rich Text Editor | Advanced | Reusable CMS management module. | 3 Days
9 | Authentication | Create Authentication Flow UI | Develop login, signup, forgot password, reset password, and OTP verification pages with validation and responsive layouts. | Authentication UI, Form Validation | Intermediate-Advanced | Complete frontend authentication system. | 2 Days
10 | Checkout | Develop Multi-Step Checkout | Create a complex checkout process with shipping details, delivery methods, payment selection, order summary, and validation. | Complex Forms, State Management | Advanced | Professional multi-step checkout flow. | 3 Days
11 | Optimization | Optimize Frontend Performance | Implement lazy loading, code splitting, image optimization, memoization, and route-level optimization for improved performance. | Performance Optimization | Advanced | Optimized and scalable frontend. | 2 Days
12 | API Integration | Integrate Mock APIs | Connect frontend modules with mock APIs using Axios or Fetch API and handle loading, error states, retries, and reusable service layers. | Axios, Fetch API | Advanced | Reusable API integration system. | 2 Days
13 | Theme System | Implement Dark & Light Theme | Create a global theme switching system with persistence using Context API and localStorage. | Theme Management | Intermediate | Application-wide theme support. | 1.5 Days
14 | Testing | Write Frontend Component Tests | Create unit tests for components, forms, and utility functions using React Testing Library and Vitest. | Testing, Vitest | Advanced | Stable and tested frontend components. | 2 Days
15 | Deployment | Deploy Production Frontend | Deploy the frontend application to Vercel or Netlify with environment configuration and production optimization. | Deployment, Hosting | Intermediate | Live production frontend deployment. | 1 Day